## Table 1
Research Phase Gantt Chart (26/February/2024 - 29/April/2024)
Activities | Working Weeks
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9
Graduation Project Description
Graduation Project Notification Form
NDA signed and triliplicate by 3 parties
Research Proposal
Project Plan
Planning
Interview with Company Supervisor, Stakeholders, Owner and Cybersecurity Consultant to determine requirements
Setting up LaTeX environment for document editing
Initial meeting with the School Lecturer to determine Requirement Analysis
Set up Azure DevOps environment (developers and stakeholders account) & GCP Firebase E-mail Account
Studying the QaaS app front-end (Flutter code)
Studying the back-end code (Node.js server, Firebase console, cloud functions, and other services utilized)
Studying and reading the SentinelOne API documentation
Studying and reading the documentations of N-Central for API monitoring
Studying and reading the documentations of Pax8 for API monitoring
Studying and reading the documentations of Bodyguard for API monitoring
Studying and reading the documentations of for API monitoring
School Lecturer Visit
Making SRS, FO, PRS, with Class Diagram, Sequence Diagram, Use Case Diagram, Activity Diagram (optional)
Monthly Report
Sprint Review for Company Supervisor
Research Report excluding Realization, Conclusions & Recommendations, and Evaluation chapters

## Table 2
Realization Phase Gantt Chart (29/April/224 - 8/July/2024)
Activities | Working Weeks
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9
Determine Definition of Done with Company Supervisor
Setting up the SCRUM board in Azure DevOps
Determine Story Points
Create Sprints
Create Product Backlogs
Create Burndown Charts
Code in the front-end client-side Flutter test environment
Code in the back-end server-side Node.js and Firebase cloud environment
Updating Research Report and filling out the missing chapters
Research Report check with Company Supervisor
Daily Stand-ups
Sprint Restrospective
Sprint Review
Unit Testing
Bugs finding and fixing
Finalizing the final product
Deploy the final product in Firebase hosting
Monthly Report
Sprint Review document for Company Supervisor
Research Report (initial draft)
Research Report (final draft)
End-presentation (colloquium)